## Sheet1
Months/Sign of Project | 1 | 2 | 3 | 4 | 5 | 6
Study and Planning
Requirement Gathering and analysis
System Design
Implementation
Testing
Documentation
Presentation and Report submission
| S>N | Weeks/Stages of project | Start Date | End Date | Duration
| 1 | Study and Planning | 2023-07-02 | 2023-08-02 | 31
| 2 | Requirement Gathering And Analysis | 2023-07-15 | 2023-09-10 | 57
| 3 | System Design | 2023-09-01 | 2023-10-01 | 30
| 4 | Implementation | 2023-10-01 | 2023-12-13 | 73
| 5 | Testing | 2023-11-15 | 2023-12-05 | 20
| 6 | Documentation | 2023-07-02 | 2023-12-13 | 164
| 7 | Presentation And Report Submission | 2023-12-10 | 2023-12-13 | 3